## Sprint2
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 02.04.2024 - 16.04.2024
Group Number |  | 33
Participant 1 |  | Vural, Zeliha
Participant 2 |  | Windhager, Wendelin
Participant 3 |  | Xu, Haoxuan
Participant 4 |  | Shehab, Mahmoud
Participant 5
Mentor |  | Oswald, Lena Esther
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Datenbankseite erstellen&einbinden | 2 | 2 | 0 | yes
2 | Daten in Datenbank speichern | 6 | 5 | -1 | yes
3 | Benutzerrollen definieren&Berechtigungen festlegen | 3 | 3 | 0 | yes
4 | Passwortverschlüsselung hinzufügen | 3 | 2 | -1 | yes
5 | Client und Serverseitig Formulare überprüfen | 4 | 4 | 0 | yes
6 | Entwerfen des Layouts für die Profilansicht | 4 | 5 | 1 | yes
7 | Tutoren-Seite erstellen | 6 | 5 | -1 | yes
8 | Tutor: Profilansicht Seite erstellen | 8 |  |  |  | no | die Profilansicht-Seite wurde erstellt; die übrigen Funktionen befinden sich noch im Fortschritt
6 |  |  |  | -1 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol