## Tabelle1 (3)
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 08.03.2024 - 02.04.2024
Group Number |  | 33
Participant 1 |  | Vural, Zeliha
Participant 2 |  | Windhager, Wendelin
Participant 3 |  | Xu, Haoxuan
Participant 4 |  | Shehab, Mahmoud
Participant 5
Mentor |  | Oswald, Lena Esther
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Startseite erstellen | 8 | 9 | 1
2 | Navbar&Footer erstellen | 6 | 4 | -2
3 | Hilfeseite erstellen | 4 | 3 | -1
4 | Impressum erstellen | 4 | 4 | 0
5 | Loginseite erstellen | 6 | 3 | -3
6 | Registrierung erstellen | 6 | 4 | -2
6 |  |  |  | -7 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 08.03.2024 - 02.04.2024
Group Number |  | 33
Participant 1 |  | Vural, Zeliha
Participant 2 |  | Windhager, Wendelin
Participant 3 |  | Xu, Haoxuan
Participant 4 |  | Shehab, Mahmoud
Participant 5
Mentor |  | Oswald, Lena Esther
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Startseite erstellen | 8 | 9 | 1 | Yes |  | Datei "index.php" enthält den Html-Grundgerüst für die Startseite. Alle Inhalte der Startseite werden hier eingefügt.
2 | Navbar&Footer erstellen | 6 | 4 | -2 | Yes |  | Navigationsleiste und Fußbereich, Styling sind in "styles.css"
3 | Hilfeseite erstellen | 4 | 3 | -1 | Yes |  | Inhalt für Hilfeseite, über Navbar erreichbar
4 | Impressum erstellen | 4 | 4 | 0 | Yes |  | Impressumsinfos, über Navbar erreichbar.
5 | Loginseite erstellen | 6 | 3 | -3 | Yes |  | Formular für Benutzeranmeldung, Weiterleitung für Anmeldung.
6 | Registrierung erstellen | 6 | 4 | -2 | Yes |  | Formular für neue Benutzer, Registrierung möglich.
6 |  |  |  | -7 | 6 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol