## Sprint5
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 15.05.2024 - 28.05.2024
Group Number |  | 33
Participant 1 |  | Vural, Zeliha
Participant 2 |  | Windhager, Wendelin
Participant 3 |  | Shehab, Mahmoud
Mentor |  | Oswald, Lena Esther
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | User anzeigen&löschen&bearbeiten&deaktivieren Seiten implementieren | 8 | 6 | -2 | yes
2 | Tutor anzeigen&löschen&bearbeiten&deaktivieren Seite implementieren | 6 | 6 | 0 | yes
3 | Adminseite backend&frontend alles fertig implementieren | 2 | 3 | 1 | yes
4 | Student anzeigen&löschen&bearbeiten&deaktivieren Seite implementieren | 4 | 4 | 0 | yes
5 | Adminindex&Navbar Fehler beheben | 3 | 2 | -1 | yes
6 | Frontend für andere Seiten implementieren | 3 | 5 | 2 | yes
7 | Kurse anzeigen&löschen&bearbeiten&deaktivieren Seite implementieren | 4 | 3 | -1 | yes
7 |  |  | 0 | -1 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol