## Sprint6
Sprint Review Protocol
Sprint No: |  | 6
Date & Time |  | 29.05.2024 - 11.06.2024
Group Number |  | 33
Participant 1 |  | Vural, Zeliha
Participant 2 |  | Windhager, Wendelin
Participant 3 |  | Shehab, Mahmoud
Mentor |  | Oswald, Lena Esther
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Bugfixes + Links Verbesserungen | 2 | 2 | 0 | yes
2 | Buchungslogik | 3 | 3 | 0 | yes
3 | Navbar bezüglich Rollen erweitern | 2 | 1 | -1 | yes
4 | Benutzer Kurse buchen Logik umsetzen | 3 | 3 | 0 | yes
5 | Tutor Kurs erstellen Logik umsetzen | 3 | 3 | 0 | yes
6 | Tutorseite und Profilseite fixen und erweitern | 3 | 4 | 1 | yes
7 | Kurserstellungen erweitern | 3 | 2 | -1 | yes
8 | Datenbank anpassen | 1 | 1 | 0 | yes
9 | ReadMe updaten | 1 | 1 | 0 | yes
10 | Frontend für alle Seiten implementieren+anpassen | 18 | 20 | 2 | yes
11 | Sprint 7 besprechen | 3 | 2 | -1 | yes
11 |  |  |  | 0 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol